## Corporate
Pages - 25
Components - 50
Pages & Components | Mockup available (Zeplin) | HTML (Web) | HTML (Mobile) | Shared to Indosat On | Reviewed by Indosat | Dev handover Date | Dev Team Handover | URLs
Master Page ( 5 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp-master.html
Component 1: Personal - Header (main-header & Mega menu) | Yes | Done | Done
Component 2: Hero banner (global_hero_carousal) | Yes | Done | Done
Component 3: Global Footer (global-contact )
Component 4: Global Footer (indo-main-footer ) | Yes | Done | Done
Component 5: Back to top | Yes | Done | Done
Component 6: Indira Icon chat bot icon | Yes | Done | Done
Component : Mini Hero baneer ( global_mini_carousal ) | Yes | Done | Done
Corp - Landing ( 4 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp-index.html
Component 1: Our Company ( pg2-comp-multilinetext ) | Yes | Done | Done
Component 2: Investor Relations ( pg2-comp-multilinetext ) | Yes | Done | Done
Component 3: Don't miss our update ( p-home-swp-03 ) | Yes | Done | Done
Component 4: Corporate Social Responsibility ( corp-abt-hddesc-cards-comp ) | Yes | Done | Done
Corp - Our Comapny - Landing ( 4 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp-ourc-landing.html
Component : Don't miss our update ( p-home-swp-03 ) | Yes | Done | Done
Component : Company history ( corp-abt-thumb-slider ) | Yes | Done | Done
Component : Company Structure ( corp-abt-cstr ) | Yes | Done | Done
Component : Financial Information ( corp_abt_Other_info ) | Yes | Done | Done
Corp - Investor Relation - Landing ( 6 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp-cir-landing.html
Component : Financial Information ( corp_abt_Other_info ) | Yes | Done | Done
Component : Good Corporate Governance ( corp-abt-hddesc-cards-comp ) | Yes | Done | Done
Component : Related Information ( corp-abt-hddesc-cards-comp ) | Yes | Done | Done
Component : Dividen & Ratings ( corp_abt_Other_info ) | Yes | Done | Done
Component : Need more info? ( c-moreinfo ) | Yes | Done | Done
Corp - Investor Relation - Dividen History ( 1 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp-cir-dividen.html
Component : Text & Graph ( rating-graph-cont ) | Yes | Done | Done
Corp - Investor Relation - Ratings ( 2 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp-cir-rating.html
Component : Institution ( c-rating-inst-cont ) | Yes | Done | Done
Component : Table ( c-rating-table-cont ) | Yes | Done | Done
Corp - Investor Relation - Financial Information ( 1 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp-cir-financial-info.html
Component : Tabs (c-reqinfo-tabs-single ) | Yes | Done | Done
Corp - Investor Relation - Good Corporate Governance ( 1 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp-cir-governance.html
Component : Tabs ( c-reqinfo-tabs-single ) | Yes | Done | Done
Corp - Investor Relation - Investor Relation Contact ( 2 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp-cir-relation.html
Component : ( corp_abt_Other_info ) ( Model Popups ) | Yes | Done | Done
Corp - Investor Relation - Request for Information ( 1 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp-cir-reqinfo.html
Component : Tabs ( c-reqinfo-tabs ) | Yes | Done | Done
Corp - Investor Relation - Shareholder ( 1 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp-cir-shareholders.html
Component : Tabs ( corp-abt-cstr-img-cont ) | Yes | Done | Done
Corp - Media - Landing ( 2 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp-media-landing.html
Corp - Media - Press Release ( 2 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp-media-press-release.html
Corp - Media - Press Release Detail ( 2 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp-media-press-release-detail.html
Corp - Our Company - Board of Commisioner ( 1 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp_oc_boardofcommisioner.html
Corp - Our Company - Board of Commisioner Detail ( 1 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp_oc_commisioner_detail.html
Corp - Our Company - CEO Message ( 1 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp_oc_ceomessage.html
Corp - Our Company - Director, Chief & Commisioner ( 1 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp_oc_director_chief.html
Corp - Our Company - Director, Chief Details ( 1 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp_oc_director_chief_details.html
Corp - Our Company - Strategy Value ( 2 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp_oc_visi_strategy_value.html
Corp - Our Company - Other Info ( 2 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/crop-ourc-other-information.html
Corp-csr-Landing(3 Components) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/corp-csr-landing.html
Component : Hero Global Carousal | Yes | Done | Done
Component : csr-bgimgright-infoleft | Yes | Done | Done
Component : csr-bgimgleft-inforight | Yes | Done | Done
Corp-csr-Pillar Education(2 Components) | Yes | [6 empty] | https://indosat-corp-portal-211f9.web.app/corp-csr-pillar-edu.html
Component : Hero Global Carousal | Yes | Done | Done
Component : csr-two-column-cards | yes | Done | Done
Corp-csr-Id-Camp(2Components) | Yes | [6 empty] | https://indosat-corp-portal-211f9.web.app/corp-csr-idcamp.html
Component : csr-infoleft-videoright | Yes | Done | Done
Component : imgleft-campinforight | Yes | Done | Done
Corp-csr-Id-Camp-inner(2Components) | Yes | [6 empty] | https://indosat-corp-portal-211f9.web.app/corp-csr-idcamp-inner.html
Component : csr-twocolumn-campinfo | Yes | Done | Done
Component : csr-carousal-popup-gallery | Yes | Done | Done

## Business
Pages - 30
Components - 66
| Pages & Components | Mockup available (Zeplin) | HTML (Web) | HTML (Mobile) | Shared to Indosat On | Reviewed by Indosat | Dev handover Date | Dev Team Handover | URLs
1 | Master Page ( 5 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/master.html
Component 1: Personal - Header (main-header & Mega menu)
Component 2: Hero banner (global_hero_carousal)
Component 3: Global Footer (global-contact )
Component 4: Global Footer (indo-main-footer )
Component 5: Back to top
Component 6: Indira Icon chat bot icon
Component : Mini Hero baneer ( global_mini_carousal )
Component : Subscription Popup
2 | Business - Home Page (Index) ( 2 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-index.html
Component : Selamat datang ( p-home-swp-03 )
Component : Selamat datang ( c-moreinfo )
3 | Business - Profile ( 3 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-profile.html
Component : Public Sector ( combo-title )
Component : Mobile ( p-home-swp-03 )
Component : Managed Service ( corp-abt-hddesc-cards-swiper )
4 | Business - Profile - Filters ( 1 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-profile-filters.html
Component : Managed Service ( corp-abt-hddesc-cards-swiper )
5 | Business - Landing Page ( 3 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-landing.html
Component : Don't miss our ( p-home-swp-03 )
Component : Produk kami ( corp-abt-hddesc-cards-swiper )
Component : Temukan ( b2b-swiper-01 )
6 | Business - Why us ( 3 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-whyus.html
Component : Sekilas tentang ( pg2-comp-multilinetext)
Component : IT Services Certification ( corp-abt-hddesc-cards-swiper )
Component : More ( c-moreinfo py-72 )
7 | Business - Product - Landing (2 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-prodcut-landing.html
Component : Stickey scroll ( single-page-scroll-sec )
Component : Mobile ( p-home-swp-03 )
8 | Business - Product - Smart Phone Bundling (3 Components ) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business_product_smart_phone.html
Component : Stickey scroll ( temp4-row )
Component : Mobile ( global_tabs_one )
Component : Mobile ( global_product_hcard )
9 | Business - IOT - Landing (1 Component) | Yes | Done | Done
| Component : Cards Grid ( multi-rows-swp-01 ) | [7 empty] | https://indosat-corp-portal-211f9.web.app/business-iot-landing.html
10 | Business - Support - Contact us(1 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-contact.html
Component : Cards Grid ( b-partnarship )
11 | Business - Support - Corp Payment (2 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-payment.html
Component : Tentang ( head-cont-section )
Component : Mudah dalam ( pg2-comp-multilinetext )
12 | Business - Support - Testimonials (1 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-product-testimonial.html
Component : swiper ( p-home-swp-03 )
13 | Business - update - Blogspot (1 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-update-blogspot.html
Component : Blog ( activity-camp )
14 | Business - update - Case Studies (1 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-explore-case-study.html
Component : Blog ( activity-camp )
15 | Business - update - Case Studies -detail (1 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-explore-case-study-detail.html
Component : ( pg2-comp-multilinetext)
16 | Business - update - connex (1 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-update-connex-webinar.html
Component : Blog ( pg2-comp-multilinetext )
17 | Business - update - Connex Webinar Series (1 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-update-connex-series.html
Components: ( activity-camp )
18 | Business - Become a partner (1 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-partner.html
Component : Let's join as our partner ( heading-info-section )
Component : Let's join as our partner ( b-partnarship-rect )
Component : Let's join as our partner ( success popup )
19 | Business - Data Center (4 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business_b2b_data_center.html
Components : p-home-swp-03 data_center_gmap b2b-data-center-swiper temp4-row
20 | Business - Disaster Recovery (4 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business_disaster_recovery-gmap.html
Components : card-list-swp-01 disaster_recovery_center_map pg2-comp-multilinetext temp4-var1
21 | Business - Media - Awards (1 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-media-awards.html
Components : corp-media-awards
22 | Business - update - News Room (1 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-update-newsroom.html
Componet : activity-camp
23 | Business - update - News Room - Detail (1 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-update-newsroom-detail.html
Componet : camp-detail
24 | Business - support (2 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-support.html.html
Components : pg2-comp-multilinetext corp_abt_Other_info
25 | Business - Product information (3 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-product-feature.html
Components : temp4-row feature3 temp4-swp-04-card-4
26 | Business - Other Information (2 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-product-other-information.html
Components : c-rating-table-cont product-how-works
27 | Business - How it works (1 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-product-howitworks.html
Components : howitwork1 howitwork2
28 | Business - General Service (2 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-product-general-service.html
Components : multi-rows-swp-01 multi-rows-swp-01-container
29 | Business - General Service (2 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-product-general-implementation.html
Components : card-list-swp-01-swiper-container multi-rows-swp-01-container
30 | Business - FAQ (1 Component) | Yes | Done | Done |  |  |  |  | https://indosat-corp-portal-211f9.web.app/business-product-general-faqs.html
Components : card-list-swp-01-swiper-container multi-rows-swp-01-container

## Personal
Pages - 90
Pages & Components | Mockup available (Zeplin) | HTML (Web) | HTML (Mobile) | Shared to Indosat On | Reviewed by Indosat | Dev handover Date | Dev Team Handover | URLS
Master Page ( 5 Components ) | Yes | Done | Done | 2020-08-25 |  |  |  | https://indosat-corp-portal-211f9.web.app/master.html
Component 1: Personal - Header (main-header & Mega menu)
Component 2: Hero banner (global_hero_carousal)
Component 3: Global Footer (main-header)
Component 4: Back to top
Component 5: Indira Icon chat bot icon
Personal - Landing ( 8 Components ) | Yes | Done | Done | 2020-08-24 |  |  |  | https://indosat-corp-portal-211f9.web.app/index.html
Component 1: What are you looking for ( p-home-list-01 )
Component 2: So much fun ( p-home-swp-01 )
Component 3: Explore our digital ( p-home-swp-02 )
Component 4: See other digital ( p-home-list-02 )
Component 5: Don't miss our update ( p-home-swp-03 )
Component 6: on myIM3 app (p-global-banner-01)
Component 7: What are you waiting (p-home-card-01)
Component 8: Have a question? (global-contact)
Search Page ( 6 Components ) | Yes | Done | Done | 2020-08-25 |  |  |  | https://indosat-corp-portal-211f9.web.app/global-search-results.html
Component 1 : Search Form
Component 2 : Support
Component 3 : Press Release
Component 4 : Document
Component 5 : Pages
Component 6 : pagination
No search results page ( 1 Components ) | Yes | Done | Done | 2020-08-25 |  |  |  | https://indosat-corp-portal-211f9.web.app/global-search-noresults.html
Component 1 : No results
Modal popups ( 2 Components ) | Yes | Done | Done | 2020-08-25
Component 1 : banner-promo-a
Component 2 : banner-promo-b
Toaster all page ( 4 Components ) | Yes | Done | Done | 2020-08-25 |  |  |  | https://indosat-corp-portal-211f9.web.app/toaster-all.html
TEMPLATE - GENERAL - 2 ( 19 Components ) | Yes | Done | Done | 2020-08-27 |  |  |  | https://indosat-corp-portal-211f9.web.app/general-component-2.html
TEMPLATE - GENERAL - 3 ( 10 Components ) | Yes | Done | Done | 2020-08-27 |  |  |  | https://indosat-corp-portal-211f9.web.app/general-component-3.html
TEMPLATE - GENERAL - 4 ( 18 Components ) | Yes | Done | Done | 2020-08-28 |  |  |  | https://indosat-corp-portal-211f9.web.app/general-component-4.html
TEMPLATE - GENERAL - 5 ( 14 Components ) | Yes | Done | Done | 2020-08-28 |  |  |  | https://indosat-corp-portal-211f9.web.app/general-component-5.html
Mobile
Prepaid
personal-mobile-landing | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-landing.html
Components : global_mini_carousal corp-abt-hddesc-cards-comp p-home-swp-01
personal-mobile-prepaid-landing | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-prepaid-landing.html
Components : corp-abt-hddesc-cards-swiper
personal-mobile-prepaid-voucherplan | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-prepaid-voucherplan.html
Components : b2b-swiper-01 temp4-swp-04-card-4 faqs-compo c-moreinfo
personal-mobile-extra-landing | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-extra-landing.html
Components : corp-abt-hddesc-cards-comp
Postpaid
Prepaid-Landing | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-postpaid-landing.html
Components : pg2-comp3-backgroundimg corp-abt-hddesc-cards-comp
Prepaid Unique Template | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-postpaid-unique-template.html
Components : pg2-comp-multilinetext postpaid-simulate-discount faqs-compo c-moreinfo
ROAMING | [7 empty] | https://indosat-corp-portal-211f9.web.app/personal-mobile-inter-callsms-landing.html
call sms - Landing | Yes | Done | Done | 2020-09-16
Components : corp-abt-hddesc-cards-comp
call sms - promo1 | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-inter-callsms-promo1.html
Components :
call sms - promo1 | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-inter-callsms-promo2.html
Components :
Roaming - Umroh | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-roaming-umroh.html
Components :
call clear voice detail satellite | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-inter-call-clear-voice-detail-satellite.html
Components :
call clear voice | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-inter-call-clear-voice.html
Components :
Call Low Rate Detail Tariff | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-inter-call-low-rate-detail-tariff.html
Components :
Call Soudi Arabia | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-inter-call-saudi-arabia.html
Components :
Call Soudi Arabia | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-roaming-outbond-roamers-landing.html
Components :
Outbond Roaming | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-roaming-outbond-roamers-landing.html
Components :
Outbond Roaming - tariff | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-roaming-outbond-roamers-landing-tarrif.html
Components :
Outbond Roaming - Quota | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-roam-internet-roam-quota.html
Components :
Detailed Country | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-roam-internet-detail-country.html
Components :
Extra
Extra - Landing | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-extra-landing.html
Components :
Mobile Data Plan | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-extra-mdataplan.html
Components :
Pulsa Safe | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-extra-pulsasafe.html
Components :
Pulsa SOS | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-extra-pulsasos.html
Components :
SMS Collect | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-extra-smscollect.html
Components :
SMS Group | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-extra-smsgroup.html
Components :
Data Rollover | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-extra-datarollover.html
Components :
Call me back | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-extra-callmeback.html
Components :
Why us
4G Plus | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-whyus-4gplus.html
Components :
Reson | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-whyus-reason.html
Components :
4g Plus Upgrade | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-whyus-4gplus-upgrade.html
Components :
Just for you
IMclass | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-justforyou-IMclass.html
Components :
IMPoin | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-justforyou-IMPoin-cek-poin.html
Components :
IMPreneur | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-justforyou-IM_Preneur.html
Components :
zonakuota | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-mobile-justforyou-zonakuota.html
Components :
Visit indonasia | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-visit-indonesia-landing.html
Components :
Travel On | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-visit-indo-landing-travelon.html
Components :
Travel On - LOC | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-visit-indo-landing-travelon-loc-selected.html
Components :
Digital Content
Digital Content
Digital Content - landing | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-digital-content-landing.html
Components :
Sportify (nadaku) | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-dc-nadaku.html
Components :
Sportify - Detail | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-dc-spotify-detail.html
Components :
Promo | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-dc-promo.html
Components :
Partner - Landing | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-dc-product-partner-landing.html
Components :
Content - Template | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-dc-partner-content-te.html
Components :
Other Info | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-dc-partner-other-info.html
Components :
Product Overview | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-dc-partner-product-overview.html
Components :
How to Subscribe | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-dc-partner-how-to-subscribe.html
Components :
Featured- Section | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-dc-featured-section.html
Components :
MyIM3
MyIM3
MyIM3 - Landing | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-myim3.html
Components :
MyIM3 - kiosmyim3 | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-myim3-kiosmyim3.html
Components :
MyIM3 - tubes | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-myim3-tebus.html
Components :
Shop
Shop
Shop - Landing | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-shop.html
Components :
Support
Help Center | [7 empty] | https://indosat-corp-portal-211f9.web.app/personal-support-help-center.html
Help Center - Landing | Yes | Done | Done | 2020-09-16
Components :
FAQ | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-support-faq-detail.html
Components :
FAQ - Normal | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-support-faq-normal.html
Components :
FAQ - Normal | Yes | Done | Done | 2020-09-16
Components :
support-indira | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-support-indira.html
Components :
Privacy Policy | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-support-privacy-policy.html
Components :
T & C | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-support-terms-condition.html
Components :
Online Booking | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-support-web-online-booking.html
Components :
Coverage Area | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-network-coverage.html
Components :
Blog
Blog
Blog - landing | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-blog-category.html
Components :
Blog - category - list | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-blog-category-list.html
Components :
Blog - category - detail | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-blog-category-detail.html
Components :
Blog - category - detail | Yes | Done | Done | 2020-09-16
Components :
Promo
Promo
Promo - landing | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-promo.html
Components :
Promo - Detail | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-promo-detail.html
Components :
General Templates
General Templates - Landing | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-general-template-landing.html
Components :
Product - Additonalinfo | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-product-additonalinfo.html
Components :
Product - feature | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-product-feature.html
Components :
Product - general-faqs | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-product-general-faqs.html
Components :
Product - How to use | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-product-howtouse.html
Components :
Product - Other info | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-product-otherinformation.html
Components :
Product - Overview | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-product-overview.html
Components :
Product - Packages | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-product-package-general.html
Components :
Product - Product promo | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-product-promo.html
Components :
Product - Traffic result 2 | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-product-traffic-result2.html
Components :
Product - Traffic result 1 | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-product-traffic-result.html
Components :
Product - T&C | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-product-terms-condition.html
Components :
404 - Page | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/404.html
Components :
Error - Page | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/error.html
Components :
Subscription Popups | Yes | Done | Done | 2020-09-16 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-email-subscription-error.html
Components : | [7 empty] | https://indosat-corp-portal-211f9.web.app/personal-email-subscription-exist.html
https://indosat-corp-portal-211f9.web.app/personal-email-subscription-success.html
New Pages & Modified pages from Indosat
Shop - landing | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-shop.html
Components :
Network Coverage | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-network-coverage.html
Components :
Business master | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/business-master.html
Components :
Promo
Promo
Promo - landing | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-promo.html
Components :
Promo - Detail | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-promo-promodetail.html
Components :
Promo - overview | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-promo-overview.html
Components :
Promo - Other Info | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-promo-otherinfo.html
Components :
Promo - feature | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-promo-feature.html
Components :
Promo - Related product | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-promo-relatedproduct.html
Components :
Promo - Where to Buy | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-promo-wheretobuy.html
Components :
Promo - General Detail | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-promo-promo-general-detail.html
Components :
Blog
Blog
Blog - landing | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-blog-category.html
Components :
Blog - category - list | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-blog-category-list.html
Components :
Blog - category - detail | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-blog-category-detail.html
Components :
Product
Product
Product - packages | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-product-package.html
Components :
Product - Traffic results | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-prod-traffic-result-flat-call.html
Components :
Product - Traffic results - idd | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-prod-traffic-result-idd.html
Components :
Product - Traffic results - Basic Tariff | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-prod-traffic-result-roam-basic-traffic.html
Components :
Product - Traffic results - detail Tariff | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-product-package-detail-tarrif.html
Components :
Product - Sim card | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-product-simcard.html
Components :
Product - Sim card -tarrif | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-product-simcard-tarrif.html
Components :
Product - Traffic Results | [7 empty] | https://indosat-corp-portal-211f9.web.app/personal-product-traffic-result-1.html
Components : | [7 empty] | https://indosat-corp-portal-211f9.web.app/personal-product-traffic-result-2.html
https://indosat-corp-portal-211f9.web.app/personal-product-traffic-result-3.html
https://indosat-corp-portal-211f9.web.app/personal-product-traffic-result-4.html
roaming - Outbond roamers | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-roaming-outbond-roamers-landing_roaming.html
Components :
roaming - Outbond roamers - traffic | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-roaming-outbond-roamers-landing_roaming-traffic.html
Components :
visit indonesia landing | Yes | Done | Done | 2020-09-22 |  |  |  | https://indosat-corp-portal-211f9.web.app/personal-visit-indonesia-landing-visit-indo.html
Components :